## ILM2 Session Plan
Time | Slide | Content | Learning Outcome | Assessment Criteria | Suggested Content | Outputs | Comments/Prompts for Dev Group
Day 1. Welcome & Introductions
930am | 1 | Programme Overview & Catch Up | n/a | n/a | Welcome, Introductions, Housekeeping | Page 1 of Handbook? | This should be self explanatory
SHOW the overview of the programme slide with both assessed and unassessed modules. Catch up with delegates re: progress with assignments to date
945am | 2 | Learning Objectives |  |  | SHOW the primary learning objectives for this three day event. 1. To develop knowledge and understanding of planning and putting team members to work on site to improve quality and team performance as required by a practising or potential site supervisor. 2. To develop knowledge and understanding of managing site plans and programme requirements that meet quality and health and safety standards to achieve plan and programme milestones as required by a practising or potential site supervisor. Discuss these in plenary
Day 1. Site Operations & Logistics
10am | 4 | Planning Work/Targets | LO1. Understand how to plan work on site | 1.1 Identify organisational targets relevant to the team | * Target setting and performance indicators (SMART and Stretch Objective Setting) * Links between Organisational and Team Objectives (The Strategic Pyramid) | Handout | Facilitator will talk us through the SMART/Stretch models and the Strategic Pyramid. Meantime - can you have a think about any models that you use or have come across before that might be useful to use?
1.2 Explain how to set SMART objectives for the team to achieve the targets
10.30am | 5 | Strategic/Tactical Objectives |  | 1.3 Describe a technique to plan to achieve the objectives | * Planning techniques appropriate to job activity - Lean Thinking and Just in Time (JIT) | Handout | Over and above Lean and JIT, can you think of any techniques you or others on your site use to plan, monitor and control activities on site?
1.4 Explain how to monitor and control a planned activity
|  | Exercise |  | S.T.O.P daily exercise personal planning techniques self reflection exercise with plenary)- TEAM- SERVQUAL- case study exercise using both JIT and Six Sigma to assess performance of site manager against SERVQUAL |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life.
11am |  | Break |  | Break
11.15am | 6 | Supply Chain/Logistics | LO1. Understand how to plan work on site | 1.5 Explain the importance of the supply chain in delivering results and meeting customer requirements | * Supply chain and logistics management in delivering results & meeting customer requirements * Monitoring and control techniques and records | Handout | Please have a think about this - do you use any specific techniques, processes or forms to monitor and record/track?
11.45am | 7 | Environmental Issues, Roles & Actions |  | 1.6 Explain how environmental issues impact upon the planning of site operations and logistics | * Use of results to “close the loop”, so ensuring that objectives are achieved * The importance of environmental protection to the organisation * The supervisor’s responsibility to implement environmental protection policies and procedures | Handout | What, if any, measures are in place on site to 'close the loop' and improve environmental performance e.g. reuse, recycling? If there are any procedures/forms/standards for environmental aspects of your work can you make a list of these please? Please have a think about what site managers responsibilities are with regards to environmental sustainability on site?
1.7 Describe what action the supervisor can take to enable the organisation to fulfil its environmental responsibilities
|  | Exercise |  | TEAM EXERCISE: Matching Supply and Demand (group work): Understanding Supply Chain planning and the risks of undersupply and oversupply. CASE STUDY. TEAM EXERCISE: Environmental Impact Assessment (EIA) Method and Technique in line with The CALA Way
12.30pm |  | Lunch |  | Lunch
1.30pm | 8 | Resource Allocation | LO2. Know how to put team members to work | 2.1 Identify resources required to complete a planned activity | * Basic project design principles & Importance of allocating clear responsibilities * Simple tools for financial appraisal of projects (Cost Benefit Analysis and PBPs) * Project planning techniques (Gantt charts, Flow charts, Network planning) * Project evaluation and review techniques (PERT) techniques * Use of objectives and targets/milestones to monitor performance and review plans | Handout | What financial tools do you use on site? What planning techniques? What evaluation techniques?
2.2 Explain how to allocate work to team members
2.3 Describe how individual performance can be improved through a clear allocation of responsibilities
2.4 Explain how to assess and support individual and team performance in achieving objectives
2.15pm | 9 | Team Exercise (Part 1) |  | TEAM EXERCISE: Project Management Exercise to demonstrate application of AC 2.1 to 2.3 - details of exercise to be agreed |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life.
3pm |  | Break |  | Break
3.15pm | 9 | Team Exercise (Part 2 & Debrief) |  | Project Management Exercise continued & debrief re: core Learning Outcomes - details of exercise to be agreed |  |  | As above
3.45pm | 10 | Performance Standards | LO3. Understand how to improve the performance of a team in delivering to plan | 3.1 Identify a possible cause of variance from a planned activity | * How to set performance standards * How to measure performance against agreed standards * Recognition and rectification of poor performance * A range of methods for measuring performance and how to select the ideal one * Techniques for performance monitoring and evaluation * How to interpret variances in performance and take appropriate action * Range of performance improvement techniques available to the supervisor | Handout | The bullet points on the left will be used by Facilitator to get a good idea of how you set, measure, recognise and rectify good/poor performance on site. Have a think about the sorts of methods/techniques you or your peers/previous managers use.
3.2 Identify actions to overcome causes of variance
3.3 Describe how to recognise and rectify poor performance
3.4 Explain how to involve team members in identifying ways to improve performance to meet objectives
|  | Team Exercise & Case Studies |  | EXERCISE ONE: Explain and analyse variance within a given scenario / EXERCISE TWO: Addressing a skills gap/performance issue in a team member using Conduct vs Capabilty matrix-develop a way forward using given case study |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life. Andy will also be looking to gather case studies from your own lived experience to use in the classroom to provide examples of where things have actually happened on CALA sites or with builders you previously worked for.
5pm |  | Final Thoughts and Close |  | Final Thoughts and Close
Day 2. Site Operations & Logistics (AM Session)
9.30am |  | Welcome back |  | Refresh of yesterday's LOs
9.45am |  | Quality Management | LO4. Understand the importance of quality management within the workplace | 4.1 Explain why quality is important to internal and external customers | * Importance to customers (internal and external) * Difference between quality assurance and quality control * Difference between design quality and process quality standards * The cost of quality and rework * The Cost, Production, Quality Triangle * Plan Do Check Act Cycle and continuous improvement and the non-conformance process | Handout | Again, Facilitator will use these bullets as a guide to extract information from you. Have a think about the cost (financial and otherwise) of quality to the business and the customer. Have you used the CPQ Triangle or the PDCA Cycle before? If so, do they work? Are there other processes you prefer?
4.2 Describe the quality system used on site
4.3 Explain how a supervisor will locate and interpret the appropriate quality specifications
|  | Team Exercise & Case Studies |  | TEAM EXERCISE: Revisit the SERVQUAL approach and use DEFENSIBLE VALUE theory exercise (the effort required to get it right and why) to cover 4.1-4.3 |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life. Facilitator will also be looking to gather case studies from your own lived experience to use in the classroom to provide examples of where things have actually happened on CALA sites or with builders you previously worked for.
11am |  | Break |  | Break
11.15am |  | Quality Management | LO4. Understand the importance of quality management within the workplace | 4.4 Explain how quality is monitored, documented and recorded on site | * Construction Assurance Process * Failure Mode Effects Analysis (FMEA) Thinking * Quality systems * The total quality management concept * Records for maintaining quality * Use of method statements to achieve required quality standards | Handout | What processes, tools, systems and/ or methods are employed by you or others on site to maange build quality?
4.5 Explain the importance of method statements in achieving the required quality standards
4.6 Explain how the supervisor can take practical and positive steps to improve quality on site
12.30pm |  | Lunch |  | Lunch
Day 2. Reading and Executing a Short-Term Programme (PM Session)
1.30pm |  | Site Planning/Programming | LO1. Understand site planning and programme requirements in order to lead and manage people and activities | 1.1 Explain the difference between a site plan and a site programme | * Planning and programming as essential elements of a construction project * The importance of documentation in the planning and programming of construction works * The relationship between planning, monitoring and control * The roles and responsibilities of the site supervisor and team leader in the planning process | Handout | Facilitator may ask here for some best practice examples of CALA site plans and programmes - be prepared to explain what makes for a good plan/programme vs a poor one. How do the roles/responsibilities of a supervisor/ASM differ from a more senior site manager with regards to planning?
1.2 Describe the roles and responsibilities of the site supervisor and team leader in the planning process
|  | Case Studies/Best Practice |  | CASE STUDY for discussion_ Examples of highly successful CALA site plans and programmes OR external + TEAM EXERCISE: Separation and ranking of Site Supervisor versus Team Leader tasks and objectives |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life. Facilitator will also be looking to gather case studies from your own lived experience to use in the classroom to provide examples of where things have actually happened on CALA sites or with builders you previously worked for.
2.15pm |  | Monitoring & Control | LO1. Understand site planning and programme requirements in order to lead and manage people and activities | 1.3 Explain the importance of the critical path and the sequencing of tasks on a programme | * The importance of effective communication and management of the project * The use of computer software in construction programming * Critical Path Analysis (CPA) and identifying work tasks, relationships and durations * Impact of level of information available, project uncertainties and other relevant factors * Importance and use of project milestones & need for regular monitoring and updating of programmes * Estimating and forecasting project expenditures | Handout | We know that lots of different types of software are used on site for progamming purposes (e.g. ASTA, Microsoft excel/project) so please try to set this aside when responding to Facilitator questions. The critical part of this aspect of development is to understand how activities are programmed well.
1.4 Explain how to ensure the programmed activities achieve the short-term goals to comply with the budget to build
|  | Team Exercise Site Project |  | TEAM EXERCISE: develop a critical path using CPA/ GANNT/ RISK/ IE (if using Teams then MsExcel can be used for GANNT) |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life.
3pm |  | Break |  | Break
3.15pm |  | Finance for Non Financial Managers | LO2. Understand the impact of managing resources, time and materials on the plan and programme | 2.5 Describe what is meant by the budget to build | * The nature and purpose of budgets, and the advantages of budgetary control * The purpose and nature of cost codes and basic cost statements * Role of the supervisor in cost control * Mechanisms to maintain control of costs, and how to select the optimum method | Handout | The purpose of this session will be to cover off the basics of managing a budget on site and why that is important re: the bigger picture.
2.6 Explain how the budget to build is used to compare actual spend on a weekly basis
5pm |  | Final Thoughts and Close |  | Final Thoughts and Close
Day 3. Reading and Executing a Short-Term Programme
9am |  | Welcome Back |  | Refresh of yesterday's LOs
9.15am |  | ILM Catch Up Session |  | Catch up on ILM requirements
9.45am |  | Resource Management | LO2. Understand the impact of managing resources, time and materials on the plan and programme | 2.1 Explain how to identify resource requirements from a plan | * Methods to monitor variance of actual performance against budget, including the budget to build * Causes of variance, their significance and ways of reducing adverse effects * How to gather information for use in determining and/or revising budgets * Methods of identifying and recording waste | Handout | Following on from the finance/budget session, this part of the course will be lookng at how to apply this knowledge in practice to monitor and control budgets on site. Can you think of key areas where budgets are adversely affected by processes procedures etc that happen on site or further upstream/downstream elsewhere in CALA?
2.2 Explain the processes involved in monitoring resource, time and material
2.3 Explain the role of standard industry outputs to inform the achievement of the plan / programme
2.4 Describe how to identify and record waste by theoretical versus actual comparisons
11am |  | Break |  | Break
11.15am |  | Work Methods | LO3. Understand different work methods and their impact on quality, health and safety and achievement of plans | 3.1 Describe two commonly used work methods | * Different types of work methods * Choice of appropriate work methods * Work methods and their impact on quality, health and safety and the achievement of plan * Preparation and implementation of method statements | Handout | This should be self-explanatory - Facilitator will be looking for examples of where method statements have been used to ensure H&S and quality are achieved on site.
3.2 Explain how the choice of work method is influenced by its impact upon quality, health and safety and achievement of plans
3.3 Explain how to prepare a simple method statement
|  | Team Exercise |  | Team Exercise on Method Statements - to be agreed |  |  | Facilitator to brief us on his thinking re: an exercise on method statements.
12.30pm |  | Lunch |  | Lunch
1.30pm |  | Management Skills | LO4. Understand how to leverage their leadership and management skills to achieve plan and programme milestones | 4.1 Explain why it is important to maintain accurate records of plant, materials and labour used on site | * The importance of maintaining optimum stocks * Methods of determining stock requirements * Stores and stock control principles and procedures * Procedures for ordering, recording receiving and issuing of materials * Maintenance of records for plant, materials, labour * Monitoring usage of plant, materials, labour * Role and responsibilities of the supervisor in managing the performance and usage of resources * Security of plant and materials | Handout | Again, Facilitator will be looking to understand CALA processes and to identify best practice examples of how you all record plant, materials and labour and order materials on site.
4.2 Explain the supervisor’s responsibilities for the ordering, receipt and storage of materials
|  | Case Studies and Exercise |  | Details of exercise / case studies to be agreed |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life. Facilitator will also be looking to gather case studies from your own lived experience to use in the classroom to provide examples of where things have actually happened on CALA sites or with builders you previously worked for.
2.30pm |  | Management Skills | LO4. Understand how to leverage their leadership and management skills to achieve plan and programme milestones | 4.3 Explain the importance of liaising with other supervisors /foremen and construction managers on a regular basis to manage interface and coordination issues | * General principles of lean production (DMAIC), six sigma, kaizen/continuous improvement etc * Importance of liaising with supervisors, foremen and construction managers * Identifying situations when work can be halted to ensure achievement of plan | Handout | This element of the course is partly about good communication and will likely overlap somewhat with a previous module. Facilitator will be looking to understand your experience in working with key stakeholders on site and to identify previous occassions where you've identified where work should be stopped temporarily in order to deliver on your plans elsewhere.
4.4 Describe two situations when work can be halted to ensure achievement of plan
|  | Self reflection exercise |  | TEAM EXERCISE: DMAIC analysis of TWO problems encountered by Teams on site (either real life examples or staged by CALA) |  |  | During the meeting we will discuss possibilities for an exercise that will be conducted in the classroom to bring above to life.
3.15pm |  | Break |  | Break
3.30pm |  | ILM Tutorial Session |  | SIGNPOST delegates to the workbook templates and walk through the content areas they should consider from this module when completing their assignments. USE PPT slide to debrief.
4.30pm |  | FINAL THOUGHTS & MODULE AWARDS |  | Thank delegates for their time and effort. Award prizes to: • THE TEAM WHO BOWLED US OVER (skittles) • THE TEAM WHO WERE REAL SMARTIES (smarties). • THE TEAM WHO WERE OUT OF THIS WORLD (mars bars/milky ways) REMIND delegates to keep in touch with their tutor, that the relevant workbooks will be circulated soon and see you at the next module
5pm |  | THANKS and CLOSE